## Revised Plan
Steps in Oracle
Sno | Activity | Custom for Singtel | Processing Step | Changes Due to HANA | Ownership | Change Description
1 | Source system sending files to Landing Pad | Yes | Inbound | Yes | Singtel | MFT + Dropbox change
2 | Landing Pad consumes the files does Transformation and Loads into Commissions Staging (ODI files) - 1. PreStage Loading 2. Informatica performs Transformation 3. ODI file is created | Yes | Inbound | Yes |  | Informatica to XDL
3 | ODI files loaded to Commissions Staging | No | Inbound | No
4 | Commissions Staging to Commission Core (V&T) Tables | No | Inbound | No
5 | Calculation Engine is executed (StageHook) | Yes | Pipeline | Yes |  | Stagehook (Oracle to HANA)
6 | Report Generation | Yes | Report Gen | Yes |  | Crystal Report (Oracle to HANA)
Steps in HANA
Sno | Activity | Custom for Singtel | Processing Step | Changes Due to HANA | Ownership | Change Description
1 | Source system sending files to Landing Pad | Yes | Inbound | Yes | Singtel | MFT + Dropbox change
2 | XDL Custom Inbound File processing 1. Consumes raw file and loads into PreStage 2. Transformation are performed by SP 3. Data moved to Commissions Staging table 4. Automatic V&T Process is initiated | Yes | Inbound | Yes |  | Informatica to XDL
3 | Calculation Engine is executed (StageHook) | Yes | Pipeline | Yes |  | Stagehook (Oracle to HANA)
4 | Report Generation | Yes | Report Gen | Yes |  | Crystal Report (Oracle to HANA)
Activity No | Testing Seq of Activities | Action Owner | Must Start on | Must End on | Dependency | Remark
1 | Run PL (Payment Process) for May 2024 and compare against Oracle | SAP | 2024-08-21 | 2024-08-21
2 | Perform May 2024 Results Comparison - Singtel | Singtel | 2024-08-22 | 25/8/2024 27/8/2024
3 | PL performance metric gathering | SAP | 2024-08-21 | 25/8/2024 27/8/2024
4 | Oracle PROD to Oracle DEV Restore Create Oracle PROD LP Dmp file Restore LP dmp into Oracle DEV LP (Without Data Masking) | Naveen/Trupti | 2024-09-03 | 2024-09-04 |  | Without Masking
5 | Oracle DEV to HANA PreProd (TCMP & EXT) Oracle LP DEV to HANA PreProd (LP) | Naveen/Krishna | 2024-09-05 | 2024-09-06 | 4
6 | Perform Data File copy to SAP SFTP Dropbox (Temp folder) - Files from Sep 3 - 8th | Trupti | 2024-09-03 | 2024-09-09
7 | Setup HANA PreProd environment | Deepan/Arjun | 2024-09-09 | 2024-09-09 | 5 | Naveen to share details
8 | Perform Data Load from Sep 3 - 8th and Resolve data load issues | SAP | 2024-09-10 | 2024-09-17 | 7
9 | Run PL (Payment Process) for Jul 2024 and compare against Oracle | SAP | 2024-09-10 | 2024-09-13 | 7 | Handover to the Singtel User Testing team
10 | UAT Briefing Session on the HANA |  | 2024-09-16 | 2024-09-17
11 | Run PL for Aug2024 | Krishna | 2024-09-16 | 2024-09-16 | 10
12 | Perform July 2024 Results Comparison - Singtel | Singtel | 2024-09-10 | 2024-09-17 | 7
13 | Load Sep month files (Sep 9 - 30) from Oracle Production | Singtel/SAP | 2024-09-18 | 2024-10-01 | 9,12
14 | Need to load Aug Adjustments (User created file) | SAP | 2024-10-02 | 2024-10-02
15 | Re-Run PL (Payment Process) for Aug 2024 and compare against Oracle | Singtel/SAP | 2024-10-03 | 2024-10-08 | 14
16 | Run PL for Sep 2024 | Singtel | 2024-10-03 | 2024-10-03 | 15
17 | Perform Aug 2024 Results Comparison - Singtel | Singtel | 2024-10-03 | 2024-10-08 | 14
Jan 2024 UT
Step 1 | Step 2 | Step 3 | Output of Step 3 | Output of Step 3 | Step 4
Raw Files | XDL (Data Transformation) - 2 | Transaction | Credits | Payout file | Reports
|  | Reference Data | Measurements
|  | Hierarchy Data | Incentives
Deposits

## Open Items
Sno | Action Items | Owner | Due Date | Status
1 | Adjustment files for June 2024 - Need adjustment Files loaded after Jul 25th, since backup was taken on Jul 25th | Neelima | 2024-09-02 | Open
2 | Timelines for activities 12,13,14,15 need to be discussed with Singtel and aligned | PM | 2024-09-03 | Open

## Plan (hidden)
Steps in Oracle
Sno | Activity | Custom for Singtel | Processing Step | Changes Due to HANA | Ownership | Change Description
1 | Source system sending files to Landing Pad | Yes | Inbound | Yes | Singtel | MFT + Dropbox change
2 | Landing Pad consumes the files does Transformation and Loads into Commissions Staging (ODI files) - 1. PreStage Loading 2. Informatica performs Transformation 3. ODI file is created | Yes | Inbound | Yes |  | Informatica to XDL
3 | ODI files loaded to Commissions Staging | No | Inbound | No
4 | Commissions Staging to Commission Core (V&T) Tables | No | Inbound | No
5 | Calculation Engine is executed (StageHook) | Yes | Pipeline | Yes |  | Stagehook (Oracle to HANA)
6 | Report Generation | Yes | Report Gen | Yes |  | Crystal Report (Oracle to HANA)
Steps in HANA
Sno | Activity | Custom for Singtel | Processing Step | Changes Due to HANA | Ownership | Change Description
1 | Source system sending files to Landing Pad | Yes | Inbound | Yes | Singtel | MFT + Dropbox change
2 | XDL Custom Inbound File processing 1. Consumes raw file and loads into PreStage 2. Transformation are performed by SP 3. Data moved to Commissions Staging table 4. Automatic V&T Process is initiated | Yes | Inbound | Yes |  | Informatica to XDL
3 | Calculation Engine is executed (StageHook) | Yes | Pipeline | Yes |  | Stagehook (Oracle to HANA)
4 | Report Generation | Yes | Report Gen | Yes |  | Crystal Report (Oracle to HANA)
Activity No | Testing Seq of Activities | Action Owner | Must Start on | Must End on | Dependency | Remark
1 | Run PL (Payment Process) for May 2024 and compare against Oracle | SAP | 2024-08-21 | 2024-08-21
2 | Perform May 2024 Results Comparison - Singtel | Singtel | 2024-08-22 | 25/8/2024 27/8/2024
3 | PL performance metric gathering | SAP | 2024-08-21 | 25/8/2024 27/8/2024
4 | Perform Data File copy to SAP SFTP Dropbox (Temp folder) - Files from Jul 26 - 31 | Singtel | 2024-08-20 | 2024-08-25
5 | Perform Data Load from Jul 26 - 31 and Resolve data load issues | SAP | 2024-08-26 | 2024-09-03
6 | Need to load June Adjustments (User created file) | SAP | 2024-09-03 | 2024-09-03 |  | need to check with singtel if they have any file - Neelima to check
7 | Unmask the masked data from oracle prod --> hana preprod | Singtel/SAP | 2024-09-03 | 2024-09-04 |  | Singtel(Trupti) to share the unmasking data and scripts (2 Unmasking scripts)
8 | Run PL (Payment Process) for Jun 2024 and compare against Oracle | SAP | 2024-09-04 | 2024-09-09 | 5,6,7 | Arjun to assist
9 | Run PL for Jul 2024 | SAP | 2024-09-10 | 2024-09-10 | 8
10 | Perform June 2024 Results Comparison - Singtel | Singtel | 2024-09-05 | 2024-09-09 | 5,6,7
11 | Perform Data File copy to SAP SFTP Dropbox (Temp folder) - Files from Aug 1 - 31 | Singtel | 2024-09-02 | 2024-09-04
12 | Load Aug month files (Aug 1 - EOM) | Singtel/SAP | 2024-09-10 | TBD | 5,8,9 | File Load per day - 2.5 hrs Capture stats for HANA - 0.5 hrs Capture stats for Oracle - 1 hrs SAP to support only in case of issues, singtel to load files
13 | Need to load July Adjustments (User created file) | SAP | 2024-09-10 | 2024-09-10 |  | need to check with singtel if they have any file - Neelima to check
14 | Re-Run PL (Payment Process) for Jul 2024 and compare against Oracle | Singtel/SAP | TBD | TBD | 12
15 | Run PL for Aug 2024 | Singtel | TBD | TBD | 13
16 | Perform July 2024 Results Comparison - Singtel | Singtel | TBD | TBD
Jul 27 - Aug 9 | File Load Process | Aug 5 - Sep 5
Aug 9 - 31 |  | Sep 5 - Sep 27
| Cutover | 2017-10-01
Jan 2024 UT
Step 1 | Step 2 | Step 3 | Output of Step 3 | Output of Step 3 | Step 4
Raw Files | XDL (Data Transformation) - 2 | Transaction | Credits | Payout file | Reports
|  | Reference Data | Measurements
|  | Hierarchy Data | Incentives
Deposits